## Sheet1
Task ID | Task Name | Category | Sub-Category | Start Date | End Date | Duration | Task Owner | Status | Dependencies
1 | Identify regulatory requirements | Envirnmental Variables | External | 2024-09-02 | 2024-09-10 | 8 | Regulatory Specialist | Not Started
2 | Conduct market research on glaucoma treatments | Envirnmental Variables | External | 2024-09-03 | 2024-09-12 | 10 | Market Analyst | Not Started
3 | Define project scope and objectives | Scope Processes | Definition | 2024-09-13 | 2025-09-15 | 3 | Project Manager | Not Started | 1, 2
4 | Develop initial project plan and WBS | Scope Processes | WBS | 2024-09-16 | 2024-09-20 | 5 | Project Manager | Not Started | 3
5 | Design AI algorithm for intraocular pressure | Organizational Systems | Team Structure | 2024-09-21 | 2024-10-01 | 10 | AI Specialist | Not Started | 4
6 | Prototype the implantable device | Organizational Systems | Team Structure | 2024-10-02 | 2024-10-12 | 10 | Bioengineer | Not Started | 5